## Sheet1
| Project Start Date | 2023-10-03 | [5 empty] | 2023-10-10 |  |  |  |  | 2023-11-14 |  |  |  | 2023-12-12 |  |  |  | 2024-01-09
| Project Name: | Bus Ticket Management System | [5 empty] | 2023-10-03 | 2023-10-10 | 2023-10-17 | 2023-10-24 | 2023-10-31 | 2023-11-07 | 2023-11-14 | 2023-11-21 | 2023-11-28 | 2023-12-05 | 2023-12-12 | 2023-12-19 | 2023-12-26 | 2024-01-02 | 2024-01-09 | 2024-01-16 | 2024-01-23
# | Activity | Assigned To | Start | End | Days | Status | %Done
1 | Project kick-off | Whole Team | 2023-10-02 | 2023-10-08 | 6 | Complete | 100 | bar: 2023-10-03
2 | Project Planning | Mehmet Aytaç & Halil | 2023-10-09 | 2023-10-28 | 19 | Complete | 100 | bar: 2023-10-10 to 2023-10-31
3 | UI / UX Design | Semih | 2023-10-29 | 2023-12-08 | 39 | Complete | 100 | bar: 2023-10-31 to 2023-12-05
4 | Designing Database System | Mehmet Aytaç & Bahadır | 2023-11-01 | 2023-12-16 | 45 | Complete | 100 | bar: 2023-10-31 to 2023-12-12
5 | Admin Panel (front-end) | Semih | 2023-12-04 | 2023-12-08 | 4 | Complete | 100 | bar: 2023-12-05
6 | Improving Interface Design #1 | Semih | 2023-12-19 | 2023-12-20 | 1 | Complete | 100 | bar: 2023-12-19
7 | Improving Interface Design #2 | Semih | 2023-12-26 | 2024-01-05 | 9 | Complete | 100 | bar: 2023-12-26 to 2024-01-02
8 | Project Documantion | Mehmet Aytaç & Halil | 2024-01-01 | 2024-01-08 | 7 | Complete | 100 | bar: 2024-01-02
9 | Payment Systems | Mehmet Aytaç | 2024-01-03 | 2024-01-04 | 1 | Complete | 100 | bar: 2024-01-02
10 | Admin Panel (back-end) | Halil | 2024-01-04 | 2024-01-08 | 4 | Complete | 100 | bar: 2024-01-02
11 | Login and Registration Database Connection | Bahadır | 2024-01-05 | 2024-01-09 | 4 | Failed | 20 | bar: 2024-01-02
12 | "Driver" Form's Features | Bahadır & Semih | - | 2024-01-09 | 0 | Failed | 50 | bar: 2024-01-09
13 | Seat Reservation Feature | Bahadır | - | 2024-01-09 | 0 | Failed | 0 | bar: 2024-01-09
14 | Bus Schedules Database Connection | Bahadır | - | 2024-01-09 | 0 | Failed | 0 | bar: 2024-01-09
STATUS CHART
Not Started
In Progress
Failed
Complete